## Slide 1
ANNUAL REPORT
2025
-26
Integrated Watershed Management
for Climate Resilience & Sustainable Livelihoods
Shramjivi Janata Sahayyak Mandal (SJSM), Satara
📍 Veloshi, Phaltan, Satara
📅 Feb – Mar 2026
👤 Mr. Suresh Kadam
Supported By Parivartan Small Grants Programme — HDFC Bank

## Slide 2
EXECUTIVE SUMMARY
Project at a Glance
The project achieved 100% completion of all primary activities during February–March 2026.
All structural and earthwork interventions met their targets, delivering immediate agricultural and water infrastructure benefits to the farming community of Veloshi, Satara.
FARMERS
Direct Beneficiaries
ACRES
Barren Land Reclaimed
STRUCTURES
Loose Boulders Built
ACHIEVED
All Targets Met
39
18
15
100%

## Slide 3
PROJECT OVERVIEW
About
This Project
Veloshi · Phaltan · Satara
2025 — 2026
PROJECT
Integrated Watershed Management for
Climate Resilience & Sustainable Livelihoods
ORGANISATION
Shramjivi Janata Sahayyak Mandal (SJSM), Satara
LOCATION
Veloshi, Block – Phaltan, District Satara, Maharashtra
PERIOD
January – March 2026 | Reporting: Feb – Mar 2026
FUNDER
Parivartan Small Grants Programme — HDFC Bank
CONTACT
Mr. Suresh Kadam (Project Manager)
Mr. Ram Kolekar (Head Operations)

## Slide 4
KEY INTERVENTIONS
Our Approach & Method
🪨
Soil Conservation
Gabion & Loose Boulder structures to manage surface runoff and prevent erosion before monsoon season.
💧
Water Management
Deepening & widening of Nalas, desilting of water bodies to improve drainage and storage capacity.
🌾
Land Reclamation
Nutrient-rich desilted soil redistributed to convert barren land into fertile agricultural plots.
🌱
Climate Resilience
Staggered Contour Trenches (SCT) to enhance groundwater recharge and reduce monsoon runoff.
👩‍🌾
Community Empowerment
Farmer Exposure Visit to demonstrate techniques and build long-term community capacity.

## Slide 5
Key Achievements & Milestones
#
Activity / Intervention
Target
Achieved
Status
1
Gabion Structures
1 No.
1 No.
✅ Complete
2
Loose Boulder Structures (LB)
15 No.
15 No.
✅ Complete
3
Staggered Contour Trenches (SCT)
4,500 m³
4,500 m³
✅ Complete
4
Desilting of Small ENB
19,000 m³
19,000 m³
✅ Complete
5
Nala Deepening & Widening
19,000 m³
19,000 m³
✅ Complete
6
Farmer Exposure Visit
1 Visit
1 Visit
✅ Complete
Achievement Rate
100%
Gabion
100%
Loose Boulders
100%
SCT
100%
Desilting
100%
Nala Work
100%
Exposure Visit

## Slide 6
OUTCOMES & IMPACT
Transforming Land.
Empowering Farmers.
39
Farmers
received nutrient-rich
desilted soil directly
18
Acres
of barren land transformed
into cultivable farmland
19K
m³
of Nala deepening &
widening completed
4,500
m³
Staggered Contour
Trenches excavated
100%
Targets
all 6 project activities
fully achieved

## Slide 7
✦ SUCCESS STORY ✦
Transforming
Barren Land
into Life
18
Acres Reclaimed
39
Families Benefited
Community Impact
Through the integrated use of 19,000 m³ of desilted soil from Nala deepening and ENB desilting works, the project successfully converted 18 acres of previously barren, unproductive land into fertile, cultivable agricultural plots — directly transforming the livelihoods of 39 farming families in the Veloshi area of Satara district.
“
The earthwork interventions have successfully met primary targets, resulting in immediate agricultural benefits for our farming community.
— Local Farming Community, Satara Watershed Region
S
Soil Recipient Group
18 acres of barren land transformed into cultivable fields via desilted soil application.
W
Watershed Stakeholders
All primary activities — Gabions, SCT, Nala widening — fully executed on schedule.

## Slide 8
PHOTO GALLERY · PART 1
Field Documentation
Soil Conservation & Water Infrastructure
Gabion Structure — Soil & Water Conservation
Nala Deepening Work
Excavation Progress
Earthwork — Ground Level
Watershed Site Overview
Site Preparation

## Slide 9
PHOTO GALLERY · PART 2
Field Documentation
Land Reclamation & Community Engagement
Community Field Work
Desilted Soil Collection
Reclaimed Land Preparation
Land Levelling
Farmer Visit
Watershed Infrastructure
Water Storage Site
Completed Site

## Slide 10
PHOTO GALLERY · PART 3
On The Ground
Structures, Earthwork & Community Participation
SCT Construction
Boulder Structure
Earthwork Progress
Agricultural Land
Final Site View

## Slide 11
Monitoring, Evaluation & Challenges
Mechanism
Frequency
Responsible
Findings/Notes
Field Visits
Regular
Mr. Suresh Kadam
Verified SCT and desilting completion
Weekly Updates
Weekly
Site Supervisors
Tracked Nala widening to 19,000 m³ target
Progress Reports
Monthly
Reporting Team
Final achievements compiled Feb–Mar 2026
Internal Audit
End of Project
Financial Auditor
Aligned with Parivartan SGP guidelines
Challenge & Resolution
⚠ Challenge
Finalising the last 1,500 m³ of Nala deepening & widening within the reporting deadline required intensive field execution and daily monitoring.
✅ Outcome: 100% of the 19,000 m³ target achieved — deadline met.
Lessons Learned
✅
Desilting + land reclamation integration proved highly effective — 18 acres converted.
✅
Structural works before monsoon ensured immediate water harvesting benefits.
💡
More frequent exposure visits recommended for deeper knowledge transfer.
💡
Soil testing of desilted material before distribution could optimise crop selection.

## Slide 12
SUSTAINABILITY & ROADMAP
Looking Forward
🎓
Capacity
Building
Conduct follow-up training for 39 farmers on sustainable agricultural practices using the 18 acres of reclaimed land.
🤝
Community
Ownership
Form Water User Groups to take long-term responsibility for maintenance of Gabion and Loose Boulder structures.
📈
Scale &
Continuity
Explore scaling the Nala deepening model to adjacent watersheds, building on 19,000 m³ success.

## Slide 13
Thank You
Shramjivi Janata Sahayyak Mandal (SJSM)
Integrated Watershed Management for Climate Resilience & Sustainable Livelihoods
📍 Veloshi, Block – Phaltan, Dist. Satara, Maharashtra
📅 Reporting Period: February – March 2026
🏦 Supported by Parivartan SGP — HDFC Bank
Annual Report | 2025 – 26 | SJSM Satara