## Slide 1
PROJECT COMPLETION REPORT · MAY 2023 – APRIL 2026
Inland Fishery Based
Livelihood Improvement
Intervention
for Tribal Community of Poladpur block, Raigad
FUNDED BY
Atlas Copco (India) Pvt. Ltd.
Corporate Social Responsibility Initiative
IMPLEMENTED BY
Shramjivi Janata Sahayyak Mandal (SJSM)
Satara, Maharashtra

## Slide 2
Table of Contents
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
2
Table of
Contents
Project Completion Report
May 2023 – April 2026
1
Cover Page
Project overview & partnership details
3
About SJSM & Project Background
Organisation profile and project context
3
Project Objectives
Goals and intended outcomes
5
Major Interventions - Overview
Nine fishery livelihood support activities
6
Fishery Operations in Detail
Hatchery, fingerling stocking, brood stock
7
Training & Capacity Building
126 programmes · 800+ participants
8
Capacity Building Achievements
Training data and key outcomes
9
Photo Gallery - Field Activities
Glimpses of interventions on ground
10
Major Achievements Summary
10 milestones with data
11
Fisheries Impact & Income Generated
270 beneficiaries · ₹1.89 Crore
12
Poladpur Block - Deep Dive
Interventions, reach & outcomes
13
Mahad Block - Deep Dive
Interventions, reach & outcomes
14
Government Scheme Access - Poladpur
485 beneficiaries · ₹3.05 Crore
15
Government Scheme Access - Mahad
235 beneficiaries · ₹1.78 Crore
16
Social Welfare & Media Coverage
Scheme linkages & newspaper coverage
17
Success Story 1 - Ranjana Pawar
From daily struggle to sustainable income
18
Success Story 2 - Gadital Cooperative
Preserving the catch, securing the future
19
Success Story 3 - Cage Culture
Innovating fisheries at Aambavade Dam
20
Cumulative Impact Summary
All outcomes across both blocks
21
Way Forward & Recommendations
Next steps and replication strategy
22
Conclusion
Closing statement and partnership acknowledgement

## Slide 3
Background & About the Project
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
3
About Shramjivi Janata Sahayyak Mandal (SJSM)
Development NGO established 1980 · Satara, Maharashtra
SJSM is a development NGO based in Satara, Maharashtra, established in 1980 by youth from nomadic tribal communities near the Koyna Dam. It has expanded to 500+ villages across Satara, Sangli, and Raigad - promoting self-reliant, community-led development.
SJSM has promoted 60 cooperatives with 27,500+ tribal families across sectors including fisheries, dairy, food processing, SHGs, herbal cultivation, and Ayurvedic medicine. Its micro-credit cooperative has 2,525 households with an annual turnover of ₹100 million.
After the Konkan floods of 2005, SJSM initiated tribal rehabilitation and inland fisheries programs for Katkari communities, forming the Konkan Lokadhikar Manch to strengthen tribal rights and advocacy.
BACKGROUND
The Katkari tribal communities of Poladpur Taluka primarily depend on inland fisheries and wage labour. Limited access to modern fishing equipment, poor post-harvest infrastructure, and declining fish productivity restricted income opportunities for fishing families.
About the Project
The project aimed to enhance the socio-economic condition of tribal fishing communities through sustainable fisheries development, capacity building, institutional strengthening, and livelihood support interventions. Implemented across 15 tribal hamlets of Poladpur Taluka (and Mahad Block), the project focused on improving fish production, strengthening cooperatives and SHGs, promoting scientific fishery practices, and increasing access to government entitlements over three years.
15
Tribal Hamlets
Covered
800+
Direct
Beneficiaries
368 HH
Baseline
Surveyed
3 Years
Project
Duration
₹6.72 Cr
Total Project
Impact
Project Objectives
1
Strengthen the traditional inland fishery-based livelihood of the Katkari tribal community.
2
Develop and implement scientific fishery management models, including stocking density and culture-based capture fisheries.
3
Strengthen local fish fingerling production units to ensure sustainable fish seed availability.
4
Increase fish production per unit area, enhancing income of local tribal fishermen.
5
Improve financial management skills and cooperative governance among fisherfolk.

## Slide 4
CHAPTER 01
Major Interventions
& Fishery Livelihood Support
Nine targeted interventions delivered to 270+ tribal fishermen across 15 hamlets in Poladpur Taluka - encompassing fishing equipment, cage culture, hatchery support, fingerling stocking, and market linkages.
4

## Slide 5
Major Interventions - Fishery Livelihood Support
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
5
A. Fishery Livelihood Support Interventions
Nine activities covering equipment, aquaculture, seed production, and market access
1
Distribution of Fishing Nets
Fishing nets distributed to fishermen & cooperative members. Training on proper usage and maintenance provided. Improved efficiency, increased catch potential, and promoted sustainable fishing practices.
2
River & Dam Fishing Nets
River and dam fishing nets provided to eligible fishermen, enabling expanded operations and access to new fishing areas. Reduced operational costs and improved fishing productivity.
3
Cage Culture Unit at Aambavade Dam
One cage culture unit established at Ambavade Reservoir. Training on cage management, fish feeding, and health monitoring. Fingerlings stocked; regular monitoring ensured healthy growth.
4
Distribution of Ice Boxes
Ice boxes distributed to fishing families to improve storage and transportation. Training on hygienic handling conducted. Reduced post-harvest losses and enabled better market prices.
5
Supply of Marketing Accessories
Marketing kits - knives, weighing scales, and plastic containers - provided to fishermen. Enhanced fish handling, storage, and marketing. Improved product quality and customer confidence.
6
Nurturing of Brood Stock
Quality brood stock of Catla, Rohu, Mrigal, and Cyprinus species procured under scientific management. Regular feeding and health monitoring ensured successful breeding cycles.
7
Stocking of Fingerlings in Reservoirs
21.5 lakh fingerlings scientifically stocked in five reservoirs over three years. Good survival and growth rates confirmed by monitoring, improving fish production and biodiversity.
8
Construction of Brood Stock Pond
Nutritious feed supplied to brood stock to improve growth, health, and reproductive performance. Training on feeding schedules and nutrition management enhanced breeding efficiency.
9
Hatchery Rearing Support
Comprehensive hatchery support through nets, haps, feed, medicines, and equipment. Improved hatchery management and larval rearing resulted in higher survival rates and increased seed production.

## Slide 6
Species
Catla, Rohu, Mrigal, Cyprinus (Indian major carps)
Brood Stock
1,000 kg quality brood stock procured and maintained
Feeding
12 months of nutritious feed supplied; training on schedules provided
Hatchery Input
Nets, haps, feed, medicines, and essential equipment provided
Breeding
Induced breeding, larval rearing, and health monitoring ensured high survival
Stocking
21.5 lakh fingerlings stocked in 5 reservoirs (242 ha) over 3 years
Fishery Operations - Hatchery, Stocking & Brood Stock
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
6
Fishery Production Operations in Detail
Hatchery unit, fish seed stocking, brood stock management, and pond construction
Fish Production Unit - Hatchery Process (Spawning · Breeding · Larval Rearing · Fingerling Production)
A total of 21.5 lakh fingerlings were scientifically stocked in 5 reservoirs covering 242 hectares during the project period (2023–2026), contributing to improved fish population and biodiversity.
Brood Stock & Hatchery Support - Key Details
Fish Seed Stocking in Reservoir
Construction of Fish Brood Stock Pond

## Slide 7
CHAPTER 02
Training &
Capacity Building
126 training and awareness programmes conducted, reaching 800+ participants across 15 tribal hamlets. From cooperative governance to tribal rights, every community group was systematically empowered.
7

## Slide 8
Training & Capacity Building
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
8
Training & Capacity Building Programmes
Systematic strengthening of fishermen, SHGs, cooperatives, and community leaders
126
Training
Programmes
800+
Participants
Reached
15
SHGs
Strengthened
300+
Fishermen
Sensitized
343
Katkari Members
Reached
#
Programme
Reach & Scale
Key Outcomes
1
Awareness on Sustainable Fishing Practices
45 camps · 300+ fishermen & Community Members 15 Tribal hamlets
Eco-friendly practices, compliance with seasonal bans, aquatic ecosystem conservation awareness.
2
Fishing Cooperative Member Training
12 programmes · 16 cooperative members trained
Enhanced governance, financial management, leadership, and adoption of modern fishing techniques.
3
Micro-Credit Cooperative Member Training
12 programmes · 20 cooperative members trained
Improved financial literacy, bookkeeping, credit management, and entrepreneurship skills.
4
SHG Capacity Building
6 programmes · 89 participants · 15 SHGs strengthened (4 new + 4 revived)
Enhanced credit access, government scheme linkages, and women's economic empowerment.
5
River Fishing Beneficiary Training
6 programmes · 32 fishermen from 42 tribal wadis
Improved fishing techniques, fish preservation, post-harvest management, river conservation.
6
Fishing Cooperative EC Members
18 sessions · 11 EC members trained
Strengthened governance, financial oversight, fisheries management, and leadership.
7
Micro-Credit Cooperative & Village Leaders
18 sessions · 15 EC + 20 village leaders
Improved decision-making, governance, financial management, and community mobilization.
8
Katkari Adivasi Aadhaar Sanghatna (KAAS)
9 programmes · 32 KAAS + 343 community members
Tribal rights awareness, government welfare schemes, social entitlements, community leadership.

## Slide 9
Capacity Building Achievements & Field Photos
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
9
Key Capacity Building Achievements at a Glance
126 training and awareness programmes conducted during the project period across all activity areas.
Over 800 participants reached through awareness camps, training programmes, and community meetings.
15 SHGs strengthened, including 4 newly formed SHGs and 4 revived inactive groups across tribal hamlets.
16 fishing cooperative members, 20 micro-credit cooperative members, 11 fisheries cooperative EC members trained.
15 micro-credit EC members, 20 village leaders, 32 river fishing beneficiaries, and 32 KAAS members directly trained.
300+ fishermen sensitized on sustainable fishing practices, seasonal restrictions, and resource conservation.
343 Katkari community members engaged through KAAS strengthening and rights-based awareness initiatives.
Glimpses of Training Activities
Baseline survey, awareness camps, SHG meetings, and capacity building sessions
SHG Capacity Building
Women's Meeting
Expert Training
Baseline Survey
Awareness Camp
Community Meeting
Training Session
Fisheries Training
Health Check-up Camp
Expert Capacity Building
Community Leader Training

## Slide 10
Major Achievements Summary
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
10
Major Achievement of Project - Summary Table
Ten key milestones achieved during May 2023 to April 2026
#
Activity
Major Milestone
Key Outcome
1
Baseline Survey
368 HH surveyed across 15 wadis
Household profiles created, documentation gaps identified, and support for accessing government schemes.
2
Dam Fishing Nets
83 fishermen supported
Increased fish catch, improved fishing efficiency, and enhanced income generation.
3
River Fishing Nets
213 fishermen supported
Expanded fishing coverage, reduced operational costs, and improved livelihoods.
4
Cage Culture Units
4 cage culture units installed
Promoted aquaculture, ensured year-round fish production, and created a sustainable income source.
5
Ice Boxes
25 SHG members supported
Reduced post-harvest losses, improved fish quality, and increased market value.
6
Marketing Accessory Kits
25 kits distributed
Improved fish handling, hygiene, weighing accuracy, and marketing efficiency.
7
Brood Stock Procurement
1,000 kg brood stock procured
Strengthened fish breeding, seed production, and long-term fish stock sustainability.
8
Fingerling Stocking
21.5 lakh in 5 reservoirs (242 ha) over 3 years
Enhanced fish population, improved biodiversity, and increased fisher incomes.
9
Brood Stock Feed
Feed provided for 12 months
Improved fish growth, breeding performance, and hatchery productivity.
10
Hatchery Rearing Support
Nets, haps, feed, medicines, equipment provided
Increased fish seed production, reduced mortality, and strengthened hatchery operations.
Overall: These fishery livelihood interventions significantly strengthened tribal fishing communities - improving fish production, reducing post-harvest losses, and contributing to greater income and economic resilience.

## Slide 11
Impact on Fisheries-Based Livelihoods
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
11
Impact on Fisheries-Based Livelihoods
During the three-year project period (2023–2026), a total of 270 fishermen directly benefited from fisheries-based livelihood interventions. Together, they harvested 1,20,552 kg of fish, generating a cumulative income of ₹1.89 Crore.
270
Direct
Beneficiaries
1,20,552 kg
Total Fish
Production
₹1.89 Crore
Total Income
Generated
Fisheries Income Generated During the Project
Category-wise breakdown of fish production and income earned
Category
Beneficiaries
Fish Production
Avg. Rate
Income Generated
River Fishing Beneficiaries
198
68,406 kg
₹155/kg
₹1,06,02,930
Dam Fishing Beneficiaries
72
52,146 kg
₹160/kg
₹83,43,360
TOTAL
270
1,20,552 kg
-
₹1,89,46,290
Key Impact Achieved
270 tribal fishermen secured sustainable livelihood opportunities through project interventions.
1.20 lakh kg of fish production achieved during the project period across 5 reservoirs.
Total income of ₹1.89 Crore generated - ₹1.06 Cr from river fishing + ₹83.4 L from dam fishing.
Improved fishing equipment, stocking, and training enhanced productivity and catch efficiency.
Increased fish availability strengthened local markets and improved household food security.
Project contributed to greater economic resilience and improved living standards among tribal families.
Fisherman in Active Fishing - River Catch
Fish Catch at Market - Post-Harvest

## Slide 12
CHAPTER 03
Poladpur Block
Deep Dive
Comprehensive coverage of interventions, capacity building, government scheme access, and community transformation specifically in Poladpur block - the primary project area.
12

## Slide 13
Poladpur Block - Interventions & Outcomes
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
Poladpur Block - Project Footprint & Outcomes
Primary project block · 15 tribal hamlets · Raigad district, Maharashtra
15
Hamlets
Covered
213
River Net
Beneficiaries
83
Dam Net
Beneficiaries
485
Govt. Scheme
Beneficiaries
₹3.05 Cr
Scheme
Benefits
Interventions in Poladpur Block
1
Fishing Net Distribution
Dam nets for 83 fishermen; river nets for 213 fishermen from 15 tribal wadis. Training on proper usage and sustainable practices.
2
Fingerling Stocking
21.5 lakh fingerlings stocked across 5 reservoirs (242 ha) - Poladpur being the primary area. Good survival rates documented.
3
Ice Boxes & Marketing
25 ice boxes to SHG members; 25 marketing kits distributed. Post-harvest losses reduced significantly.
4
Health Camp
Health check-up camps conducted for tribal fishing families - benefiting community wellbeing.
Fish Stocking Activity
Health Camp
Government Scheme Access - Poladpur Block: 485 beneficiaries · ₹3.05 Crore in benefits · Includes PMAY housing (116 families), Shabari Awas Yojana (18 families), 257 caste certificates, MSRLM revolving funds.
Distribution of Fishing Equipment - Poladpur
Fingerling Transportation for Stocking
Net Distribution Event
13

## Slide 14
CHAPTER 04
Mahad Block
Deep Dive
Community interventions, capacity building, and government scheme access in Mahad Block - the Next project area extending the project's reach to additional tribal communities.
14

## Slide 15
Mahad Block - Interventions & Outcomes
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
Mahad Block - Project Footprint & Outcomes
Next project block · Raigad district, Maharashtra
235
Govt. Scheme
Beneficiaries
₹1.78 Cr
Scheme
Benefits
62
PMAY Housing
Families
22
Shabari Awas
Families
300+
Fishermen
Sensitized
Interventions & Activities in Mahad Block
The Mahad Block was covered as the Next project area, extending the reach of the fisheries livelihood intervention to additional tribal communities. Key activities included awareness campaigns, training for fishermen and SHG members, capacity building of village leaders, and facilitation of access to government welfare schemes.
Through continuous awareness campaigns and handholding support by SJSM, 235 beneficiaries from Mahad Block accessed government welfare schemes worth ₹1.78 Crore during the project period.
Government Scheme Access - Mahad Block
PMAY Housing
62 families received housing support under Pradhan Mantri Awas Yojana
Shabari Awas Yojana
22 families benefited from this tribal housing scheme
Caste Certificates
Beneficiaries supported to obtain caste certificates and ration cards
Poultry Units
Poultry units provided to beneficiaries for income diversification
Ujjwala Gas
Ujjwala LPG Gas Connections extended to eligible beneficiaries
Community Infrastructure
Support for community infrastructure and sanitation improvement
Community Gathering - Mahad
Awareness Camp - Mahad Block
SHG Meeting in Mahad Block
Capacity Building - Mahad
Mahad Block Impact: 235 beneficiaries accessed government schemes worth ₹1.78 Crore - including housing, livelihood assets, LPG connections, and caste certificates.
E-Rickshaw Distribution - Govt. Scheme
Solar Panel Distribution - Mahad
15

## Slide 16
Government Scheme Access - Poladpur Block
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
16
Government Scheme Access & Social Entitlements - Poladpur Block
485 beneficiaries · Schemes worth ₹3.05 Crore · 2023–2026
One of the most significant outcomes of the project was the increased awareness among tribal communities regarding their rights, government welfare schemes, and the importance of possessing essential documents. Through continuous awareness campaigns, training programmes, community meetings, and handholding support provided by SJSM, beneficiaries were able to access a range of government welfare schemes and social security benefits.
116
PMAY Housing Support
116 families from tribal hamlets received housing support under Pradhan Mantri Awas Yojana (PMAY). This transformative intervention provided concrete homes to families previously living in kutcha structures.
18
Shabari Awas Yojana
18 families benefited from Shabari Awas Yojana - a state-level tribal housing scheme. Combined with PMAY, this scheme provided comprehensive housing coverage to eligible tribal families.
257
Caste Certificates
257 beneficiaries obtained caste certificates, enabling access to various tribal welfare schemes, educational benefits, job reservations, and government entitlements previously inaccessible without documentation.
40
MSRLM Revolving Fund
40 women members from 4 Self-Help Groups received revolving fund support through Maharashtra State Rural Livelihoods Mission (MSRLM), enhancing financial inclusion and entrepreneurship.
485
Total Scheme Beneficiaries
Beneficiaries also accessed Ujjwala Gas Connections, Ayushman Bharat Cards, and electricity connections - collectively improving quality of life across 15 tribal hamlets in Poladpur ₹3.05 Crore
Equipment Distribution
educational material support
Solar Power Scheme
community infrastructure schemes

## Slide 17
Government Scheme Access - Mahad Block & Social Welfare
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
17
Mahad Block Scheme Access & Social Welfare Infrastructure Support
235 beneficiaries · ₹1.78 Crore · Plus social welfare linkages across both blocks
Government Scheme Distribution - Community Empowerment Event
Scheme
Beneficiaries / Units
Value / Benefit
Impact
PMAY - Pradhan Mantri Awas Yojana
62 families
Housing grant
Permanent concrete homes for tribal families
Shabari Awas Yojana
22 families
State housing grant
Tribal housing scheme; complementary to PMAY
Caste Certificates
Multiple beneficiaries
Documentation
Access to reservations, schemes, and entitlements
Ration Cards
Multiple beneficiaries
Food security
Access to PDS and subsidized food provisions
Poultry Units
Multiple beneficiaries
Livelihood asset
Income diversification beyond fishing activities
Ujjwala LPG Connections
Multiple beneficiaries
Clean cooking fuel
Reduced indoor smoke; women's health improvement
Community Infrastructure
9 hamlets
Satranji + furniture support
Physical assets for community meeting spaces
Educational Materials
9 hamlets
Furniture + supplies
Support for schools and educational infrastructure
Solar Power Scheme
5 hamlets
Solar installations
Renewable energy access for tribal hamlets
Additional Social Welfare Infrastructure Linkages
E-rickshaw units provided for livelihood transportation
Sugarcane juice extraction machines for income generation
Open gym equipment installed in tribal hamlets
Community business infrastructure support extended
Solar power scheme covered 5 hamlets across both blocks

## Slide 18
Media Coverage & Social Recognition
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
18
Media Coverage - Project in the News
Project activities gained significant media attention in local and regional newspapers
The project's community activities, government scheme distributions, and tribal empowerment initiatives received coverage in local Marathi newspapers, reflecting the public significance and community recognition of SJSM's work in Poladpur and Mahad blocks.
Marathi Newspaper Coverage - Poladpur Tribal Fisheries Project
'Prahar' Newspaper - Project Activities Coverage
Pudhari Newspaper - SJSM Tribal Empowerment Coverage
Media coverage in 'Pudhari ', 'Prahar', and local Marathi newspapers highlighted the transformative impact of fisheries interventions and government scheme access for Katkari tribal communities.

## Slide 19
CHAPTER 05
Success Stories
Community Voices
Three documented stories of transformation - a tribal fisherwoman, a 172-member cooperative, and a cage culture pioneer - demonstrating the human impact behind the numbers.
19

## Slide 20
Success Story 1 - Ranjana Pawar
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
20
SUCCESS STORY 1
"From Daily Struggles to Sustainable Success"
Ranjana Pawar · Fisherwoman & Cooperative Member · Poladpur Taluka
BACKGROUND
Ranjana Pawar has been engaged in fishing activities along with her family for many years as a member of the local fishing cooperative. Fishing served as the primary income source for her household. However, limited access to quality fishing equipment, inadequate post-harvest facilities, and fluctuating fish catch resulted in irregular earnings and financial uncertainty.
CHALLENGES
Like many fisher families in the region, Ranjana faced difficulties maintaining stable income due to traditional fishing methods, post-harvest losses, and limited market opportunities. The lack of proper storage facilities often affected fish quality and reduced the selling price of her catch, compounding financial stress on the household.
PROJECT INTERVENTION
Under the Fisheries Livelihood Development Project by Atlas Copco India and SJSM, Ranjana received support through various livelihood enhancement initiatives. She participated in training on sustainable fishing practices, fish handling, marketing, and resource conservation. Improved fishing equipment and post-harvest support were facilitated.
CHANGE ACHIEVED: More regular earnings, reduced post-harvest losses, ability to sell fish at improved prices. Enhanced financial security and reduced dependence on seasonal wage labour. Ranjana is now a confident, active cooperative member.
The training and support provided through the project helped me improve my fishing activities and earn a more stable income. Today, I feel more confident about supporting my family through fishing.
- Ranjana Pawar, Fisherwoman and Cooperative Member, Poladpur

## Slide 21
Success Story 2 - Gadital Fishing Cooperative
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
21
SUCCESS STORY 2
“Preserving the Catch, Securing the Future”
Adiwasi Machhimar V.K. Sahakari Sanstha, Gadital - 172 Members · near Bajire Dam, Poladpur
Society Profile
Society Name:
Adiwasi Machhimar V.K. Sahakari Sanstha, Marya Gadital
Members:
172 active members
Chairman:
Mr. Kashinath Tukaram Pawar
Secretary:
Mr. Pandurang Sitaram Waghe
Location:
Gadital village, near Bajire Dam
Activity:
Inland fishing as primary livelihood
Ice Box Distribution Event - Adiwasi Machhimar V.K. Sahakari Sanstha, Gadital
THE CHALLENGE
Members of the cooperative regularly ventured into Bajire Dam reservoir to catch fish. However, due to the perishable nature of fish and the absence of cold storage facilities, unsold fish often spoiled within a day, resulting in financial losses. Fishermen were forced to sell at whatever price local traders offered.
PROJECT INTERVENTION
Under the project, Atlas Copco India and SJSM provided ice boxes to members of the fishing community. Training was conducted on hygienic fish handling, storage practices, and effective use of ice boxes to improve fish preservation and reduce post-harvest losses.
IMPACT OF CHANGE
Fish can now be stored safely for longer periods, reducing spoilage. Fishermen gained flexibility to sell in nearby and distant markets, securing better prices. Dependence on local middlemen reduced, bargaining power strengthened, and income stability increased for all 172 members.
Earlier, we had to sell fish immediately, often at whatever price was offered. With the ice boxes provided through the project, we can preserve our fish, access better markets, and earn better incomes. Our hard work now brings better returns.
- Member, Adiwasi Machhimar V.K. Sahakari Sanstha, Gadital

## Slide 22
Success Story 3 - Cage Culture Innovation
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
22
SUCCESS STORY 3
"Innovating Fisheries, Securing Futures"
Cage Culture Initiative · Aambavade Dam · Adiwasi Machhimar V.K. Sahakari Sanstha
Cage Culture System at Aambavade Dam - Full View
Cage Frame Installation Process - Community Participation
Background
The fishing community around Aambavade Dam depends primarily on fisheries for its livelihood. Declining fish availability, seasonal fluctuations, and limited access to modern aquaculture practices resulted in unstable incomes. Traditional fishing methods were insufficient due to declining fish stocks and seasonal uncertainties.
Project Intervention
Atlas Copco India provided CSR support and SJSM facilitated the establishment of a Cage Culture Unit at Aambavade Dam. Activities included: installation of fish cages, stocking of commercially valuable fish species, and technical training on cage management, feeding practices, water quality monitoring, and fish health management.
Change Achieved
Established a functional cage culture unit at Aambavade Dam
Enhanced fish production through scientific aquaculture practices
Improved technical knowledge and skills of cooperative members
Created a sustainable income source beyond traditional fishing
Promoted efficient and responsible use of reservoir resources
Strengthened long-term economic resilience of fishing households
Cage culture has opened a new avenue of income for our cooperative. With the training and support received through the project, we are now confident about adopting modern fish farming practices and building a better future for our families.
- Member, Adiwasi Machhimar V.K. Sahakari Sanstha, Aambavade
Cage Frame
Cage System
Operational Cage
The Cage Culture Initiative demonstrated how innovative fisheries interventions can transform traditional livelihoods into sustainable income-generating opportunities for tribal communities.

## Slide 23
Cumulative Impact Summary - 2023–2026
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
23
Cumulative Project Impact - May 2023 to April 2026
Comprehensive outcomes across fisheries, government schemes, training, and community development
21.5 Lakh
Fingerlings Stocked
(5 reservoirs, 242 ha)
₹1.89 Cr
Fisheries Income
Generated
₹4.83 Cr
Govt. Scheme
Benefits
720
Govt. Scheme
Beneficiaries
126
Training
Programmes
800+
Participants
Reached
Block-wise Impact Comparison
Indicator
Poladpur Block
Mahad Block
TOTAL
Govt. Scheme Beneficiaries
485
235
720
Govt. Scheme Benefits
₹3.05 Crore
₹1.78 Crore
₹4.83 Crore
PMAY Housing Families
116 families
62 families
178 families
Shabari Awas Families
18 families
22 families
40 families
Caste Certificates
257 beneficiaries
Multiple
257+
Fisheries Livelihood Impact
Category
Beneficiaries
Fish Production
Market Rate
Income Generated
River Fishing
198
68,406 kg
₹155/kg
₹1,06,02,930
Dam Fishing
72
52,146 kg
₹160/kg
₹83,43,360
TOTAL
270
1,20,552 kg
-
₹1,89,46,290
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
23

## Slide 24
Way Forward & Recommendations
SJSM · Atlas Copco CSR · 2023–2026
Project Completion Report · Inland Fishery Based Livelihood Improvement · Poladpur & Mahad, Raigad
24
Way Forward & Recommendations
In conclusion, the project has successfully boosted fishery-based livelihoods, enhancing income and community resilience. To ensure year-round self-reliance, additional support is needed to diversify livelihoods through small-scale enterprises and animal husbandry.
Extend Project Support
Provide two additional year of funding to diversify livelihoods through small-scale enterprises and animal husbandry, ensuring year-round income stability for Katkari tribal families in both blocks.
Replicate the Fishery Model
Scale the successful fishery model to adjacent Mahad and Mangaon blocks, empowering additional tribal communities toward sustainable, self-sufficient futures based on proven intervention strategies.
Strengthen Institutions
Continue capacity building of fishing cooperatives, SHGs, and community organizations to ensure long-term self-management, governance, and financial sustainability beyond the project period.
State Partnership Linkages
Explore formal linkages with Maharashtra state fisheries departments, NABARD, and government programmes for continued technical support, policy integration, and resource mobilization.
By expanding proven interventions to Mahad and Mangaon blocks, we can empower more tribal communities toward sustainable and self-sufficient futures - building on the demonstrated success of this three-year model.

## Slide 25
CONCLUSION
Three Years of
Transformative Impact
The Inland Fishery Based Livelihood Improvement Intervention, implemented by Shramjivi Janata Sahayyak Mandal (SJSM) with CSR support from Atlas Copco (India) Pvt. Ltd., has achieved significant milestones in improving the livelihoods, institutional capacities, and socio-economic conditions of Katkari tribal fishing communities in Poladpur Taluka and Mahad Block, Raigad district.
Over three years (May 2023 – April 2026), the project has demonstrated that targeted investments in fisheries development - combining livelihood support, scientific fisheries management, capacity building, and institutional strengthening - can create lasting impact for marginalized tribal communities.
Together, we have demonstrated that sustainable development is achievable when communities, NGOs, and the private sector work in partnership toward a shared vision of inclusive growth. This project stands as a testament to what collective action and genuine partnership can achieve.
IMPLEMENTED BY
Shramjivi Janata Sahayyak Mandal
(SJSM), Satara
Established 1980 · Maharashtra
FUNDED BY
Atlas Copco (India) Pvt. Ltd.
Corporate Social Responsibility Initiative
Project Period: May 2023 – April 2026
· For Corporate Presentation Only · © 2026 SJSM & Atlas Copco (India) Pvt. Ltd.