TE Integrated Watershed Management Project (IWMP) – Ghatdare

Annual Progress Report FY 2025-26

Project Overview

| Detail | Information |
| --- | --- |
| Project Title | TE Integrated Watershed Management Project (IWMP) Village -Ghatdare |
| Location | Ghatdare, Taluka -Khandala, District- Satara, Maharashtra |
| CSR Partner | TE Connectivity |
| Implementing Partner | Shramjivi Janata Sahayyak Mandal, Satara |
| Project Head Operations | Mr. Ram Kolekar |
| Project Launch Date | 1 April 2025 |
| Total Households | 225 |
| Total Area | 647 hectares |
| Reporting Period | 1 April 2025 – 31 March 2026 |

Background & Need

Ghatdare village has faced acute water scarcity, declining groundwater levels, and severe soil erosion that reduced agricultural productivity and increased drought vulnerability. TE Connectivity, in partnership with Shramjivi Janata Sahayyak Mandal and Gram Panchayat Ghatdare – Bhoslewadi, launched an integrated watershed program to restore water balance, reduce erosion, and make the village drought-resilient.

Project Objectives

- Increase groundwater recharge and create decentralized water storage

- Control soil erosion through ridge-to-valley treatment

- Bring 250 hectares of farmland under assured irrigation

- Provide safe drinking water to the community

- Build climate resilience and improve crop productivity

Key Activities Undertaken

- Nala Deepening & Widening: Excavation initiated using Excavator to enhance flow and storage

- Desilting of Percolation Tanks: Silt removal to restore storage capacity

- Loose Boulder Structures: Gully plugging and runoff control installations

- Gabion Structures & CCT: Continuous Contour Trenches on slopes to reduce erosion

- Water Purification Unit: Planned to provide safe drinking water

- Community Mobilization: Gram Sabha approvals, awareness sessions, and local participation

Outputs (FY 2025-26)

| Output | Target / Plan | Achievement (Actual) |
| --- | --- | --- |
| Water conservation structures constructed | Deep SCT 375 Pit Nala D&W 25,000 Cum; ENB desilt 9,635 Cum; Gabion 5; LBS 30 | Deep SCT 375 Pit Nala D&W 24,990 Cum ENB desilt 9,635 Cum Gabion 5 LBS 30 |
| Total additional water storage created (annual TCM) | 136.43 TCM | 136.43 TCM |
| Observation wells monitored | 21 wells monthly | 21 wells monitored monthly (June 2025–April 2026) |
| Households reached with awareness & mobilization | 225 households | 225 households engaged via Gram Sabha & sessions |
| Percolation tanks desilted | As per plan | Desilting completed as planned |
| Water Purification Unit | Install and commission | Planned; procurement initiated |
| Area under assured irrigation (hectares) | 647 hectares (target) | Progressive coverage; irrigation potential increased in treated zones |

Outcomes (FY 2025-26)

| Outcome | Indicator | Result / Impact |
| --- | --- | --- |
| Improved groundwater levels | Average post-monsoon rise (m) | 2.5–3.2 m rise observed across monitoring wells |
| Increased annual water availability | Additional stored water (TCM/year) | 136.43 TCM available for recharge/irrigation |
| Enhanced irrigation reliability | Hectares with assured irrigation | Significant increase in irrigation potential across 100 Ha., progress toward 647 ha target |
| Reduced soil erosion | Visual/site inspection; reduced gully progression | Erosion stabilized in treated ridge-to-valley zones; gully plugging effective |
| Improved crop productivity | Farmer reports; expected yield uplift | Early reports indicate improved soil moisture and crop prospects |
| Safe drinking water access | Water purification unit status | Unit planned; once commissioned will provide treated water to community |
| Community capacity & governance | Gram Sabha participation | 100% Village meetings approvals; local committees engaged for maintenance |
| Climate resilience | Reduced vulnerability to drought | Increased groundwater buffer and soil conservation reduce drought risk |

Water Conservation Structures – Progress Summary

| Sr No. | Activity | Plan | Actual | Water Storage TCM One Year |
| --- | --- | --- | --- | --- |
| 2.a | Deep SCT (Nos) | 375 | 375 | 18.75 |
| 2.b | Nala Deepening & Widening (Cum) | 25,000 | 24,990 | 74.97 |
| 2.c | Desilting of ENB (Cum) | 9,635 | 9,635 | 28.905 |
| 2.d | Gabion Structures (Nos) | 5 | 5 | 7.5 |
| 2.e | Loose Boulder Structures (Nos) | 30 | 30 | 6.3 |
| Total | – | – | – | 136.43 |

Groundwater Monitoring June 2025 – April 2026

- Monitoring points: 21 observation wells across Ghatdare

- Average well depth: 8–9 meters

- Post-monsoon rise: Average water level rise 2.5–3.2 meters (July–October 2025)

- Seasonal low: February–March 2026 showed lowest levels during dry season

- Highest recharge zones: Areas adjacent to Nala Deepening and Desilting of small ENB Site

- GPS coverage: Latitude 18.0157–18.0186; Longitude 74.0693–74.0712

Alignment with UN Sustainable Development Goals

| SDG | Project Contribution |
| --- | --- |
| SDG 6 Clean Water and Sanitation | Improves groundwater recharge and plans for water purification to ensure safe drinking water |
| SDG 2 Zero Hunger | Expands assured irrigation across 647 hectares to boost agricultural productivity and food security |
| SDG 13 Climate Action | Builds resilience through soil conservation, water harvesting, and sustainable land management |
| SDG 15 Life on Land | Controls soil erosion, restores degraded land, and promotes sustainable ecosystem use |
| SDG 11 Sustainable Cities and Communities | Strengthens local governance and community participation through Gram Sabha processes |
| SDG 17 Partnerships for the Goals | Demonstrates multi-stakeholder collaboration between corporate CSR, implementing NGO, and local governance |

Conclusion

The TE Integrated Watershed Development Project – Ghatdare delivered measurable outputs (structures, desilting, monitoring, community mobilization) and achieved early outcomes (substantial groundwater recharge, increased water storage, improved irrigation potential, and strengthened community governance) in FY 2025-26. Completing the water purification unit, scaling irrigation interventions, and measuring crop yield changes will consolidate gains and demonstrate long-term impact aligned with SDGs.