| Field | Details (to be filled) |
| --- | --- |
| NGO Name | Shramjivi Janata Sahayyak Mandal Satara |
| Report Title | Project Annual Report |
| Project Name | Integrated Watershed Management for Climate Resilience and Sustainable Livelihoods |
| Project Location(s) | Veloshi, Block – Phaltan Dist. -Satara |
| Implementation Period | 2025-2026 |
| Reporting Period | January 2026 to March 2026 |
| Contact Details | Mr. Ram Kolekar – Head Operations Mobile - |
| Date of Submission | 30 March 2026 |

Table of Contents

- Executive Summary

- Project Overview & Background

- Objectives & Scope

- Key Interventions & Approach

- Key Achievements & Milestones

- Outcomes & Impact

- Financial Summary

- Challenges & Mitigation Strategies

- Lessons Learned & Best Practices

- Sustainability & Future Roadmap

- Monitoring and Evaluation Plan

- Government Collaborations (if any)

- Community Contribution (if any)

- Events & Campaigns (with Media Coverage)

- Case Studies & Success Stories

- Community Feedback & Testimonials

- Appendices

1. Executive Summary

The project reached a final milestone during the January 2026 To March 2026 reporting period with the 100% execution of all proposed primary activities. All structural and earthwork interventions have met their targets, providing immediate agricultural benefits such as land reclamation and enhanced water storage for the local farming community.

2. Project Overview & Background

- Project Background: An initiative dedicated to integrated watershed management to build climate resilience and support sustainable livelihoods.

- Project Scope: Geographic focus on Satara involving structural water management and extensive earthwork.

- Beneficiary Profile: Local farmers benefiting from land transformation and improved water infrastructure.

- Total Beneficiaries: 39 farmers have directly benefited from the project's soil distribution and land preparation activities.

3. Objectives & Scope

- Primary Objectives: To implement sustainable watershed interventions that mitigate climate risks and empower the local agricultural community.

- Secondary Objectives: To reclaim barren land and improve groundwater recharge through physical structures.

4. Key Interventions & Approach

- Soil Conservation: Construction of Gabion and Loose Boulder structures to manage runoff.

- Water Resource Management: Deepening and widening of Nalas and desilting of existing water bodies.

- Land Reclamation: Use of excavated desilted soil to transform barren land into fertile agricultural plots.

5. Key Achievements & Milestones

| Activity/Target | Planned/Target | Achieved | Remarks/Notes |
| --- | --- | --- | --- |
| Gabion Structures | 1 No. | 1 No. | Successfully completed. |
| Loose Boulders (LB) | 15 No. | 15 No. | All 15 structures completed. |
| Staggered Contour Trenches (SCT) | 4,500 Cum. | 4,500 Cum. | Full achievement reached. |
| Desilting of small ENB | 19,000 Cum. | 19,000 Cum. | Successfully achieved. |
| Nala Deepening and Widening | 19,000 Cum. | 19,000 Cum. | Final target fully achieved. |
| Exposure Visit | 1 | 1 | Completed to date. |

6. Outcomes & Impact

- Land Reclamation: 18 acres of previously barren land transformed into cultivable agricultural land.

- Resource Efficiency: Nutrient-rich desilted soil utilized effectively for land preparation.

- Climate Resilience: Completed 19,000 cubic meters of Nala work to improve water drainage and storage.

7. Challenges & Mitigation Strategies

- Challenge: Finalizing the last 1,500 cubic meters of Nala deepening and widening by the reporting deadline.

- Mitigation Strategy: Intensive field execution and monitoring.

- Outcome: 100% completion of the targeted 19,000 cubic meters achieved.

Summarized Learnings:

- What Worked: The integration of desilting with land reclamation proved highly effective, as 18 acres of barren land were successfully converted into cultivable plots using nutrient-rich soil.

- What Worked: Timely execution of structural interventions (Gabions and Loose Boulders) before the monsoon season ensures immediate water harvesting benefits.

- What Didn't: Relying on a single exposure visit may be insufficient for deep community knowledge transfer; increasing frequency could enhance technical understanding.

- Recommendations: Future projects should prioritize soil testing of desilted material before distribution to optimize crop selection for the 39 benefited farmers.

Sustainability & Future Roadmap

| Pillar/Strategy | Actions/Plans |
| --- | --- |
| Capacity Building | Conduct follow-up training for the 39 farmers on sustainable agricultural practices using the reclaimed land. |
| Community Ownership | Form "Water User Groups" to take responsibility for the long-term maintenance of the completed Gabions and Loose Boulder structures. |
| Scale & Continuity | Explore scaling the nala deepening model to adjacent watersheds, building on the successful completion of 19,000 cubic meters. |

Monitoring, Evaluation & Compliance

| Mechanism/Tool | Frequency | Responsible | Notes/Findings |
| --- | --- | --- | --- |
| Field Visits | Regular intervals | Project Manager (Mr. Suresh Kadam) | Verified completion of SCT and desilting activities. |
| Weekly Updates | Weekly | Site Supervisors | Tracked the progress of nala widening until the final 19,000 cubic meter target was met. |
| Dashboards/Decks | Monthly | Project Management Unit | Used to visualize progress against targets, such as the 15 targeted Loose Boulder structures. |
| Monthly Progress Reports | Monthly | Reporting Team | Compiled final achievements for the February-March 2026 period. |
| Internal/External Audit | End of project | Financial Auditor | Ensures alignment with Parivartan Small Grants Program guidelines. |

Events & Campaigns

| Event/Campaign Name | Date | Description/Outcome |
| --- | --- | --- |
| Farmer Exposure Visit | February-March 2026 | One exposure visit was conducted to demonstrate watershed management techniques to local stakeholders. Village Ghatdare Block Khandala Dist. Satara |
| Land Reclamation Drive | February-March 2026 | Awareness campaign on the benefits of using desilted soil for barren land transformation. |

Case Studies & Success Stories

| Thematic Area | Case Study Title/Name | Summary/Outcome |
| --- | --- | --- |
| Education | Farmer Exposure & Technical Training | Conducted one exposure visit to educate local stakeholders on watershed management and climate resilience techniques. |
| Healthcare | Not Applicable | Focus of this reporting period was on environmental infrastructure. |
| Environment & Livelihood | Transforming Barren Land into Productive Assets | Used 19,000 cubic meters of desilted soil and 19,000 cubic meters from nala deepening to reclaim 18 acres of barren land for 39 farmers. |
| Accessibility & Inclusion | Improving Water Access for Marginalized Farmers | Completed 19,000 cubic meters of nala deepening and widening to ensure equitable water distribution and storage for the community. |
| Skill Development | Technical Watershed Construction | Local community engagement in constructing 15 Loose Boulder structures and 1 Gabion structure, building local capacity for future maintenance. |

Community Feedback & Testimonials

| Beneficiary Name/Group | Feedback/Quote | Project Area |
| --- | --- | --- |
| Local Farming Community | "The structural and earthwork interventions have successfully met primary targets, resulting in immediate agricultural benefits." | Satara Watershed Region |
| Soil Recipient Group (39 Farmers) | 18 acres of previously barren land have been successfully transformed into cultivable agricultural land through the application of desilted soil. | Reclaimed Agricultural Land |
| Watershed Stakeholders | The project reached a critical milestone with all proposed primary activities, including Gabions and SCT, fully executed. | Project Infrastructure Sites |